## Segment 1
Division | Tasks | Team | Deliverable?
Presentation | ✓ Selected topic | Shruthi | Yes
| ✓ Reason why they selected their topic | Shruthi | Yes
| ✓ Description of their source of data | Shruthi | Yes
| ✓ Questions they hope to answer with the data | Shruthi | Yes
Github | Main Branch ✓ Includes a README.md | Nora | Yes
| README.md ✓ Description of the communication protocols | Nora | Yes
| Individual Branches ✓ At least one branch for each team member | Nora | Yes
| Individual Branches ✓ Each team member has at least four commits from the duration of the first segment | All | Yes
Database | Data Collection Victoria & Kaggle | All | No
| Database Design Sample data that mimics the expected final database structure or schema | Razza/Yaz | Yes
| Data Preprocessing Transform and merge Raw Data into one final Dataset | Yaz | No
| Natural Language Processing | Nida/Shruthi | No
| Draft machine learning module is connected to the provisional database | Nida/Shruthi | Yes
ML | Build the ML Model | Faiz/Nora | No
| Takes in data in from the provisional database | Faiz/Nora | Yes
| Outputs label(s) for input data | Faiz/Nora | Yes
Dashboard | N/A |  | N/A
Documentation & Tracking | Resources.md | Yaz | No
| Action Items Tracker.xls | Yaz | No
Done
Need Help!
In Progress
Yet to start
N/A